## Test Plan
Test Schedule | Resources | Approval
Test Plan Review: | Test Manager: [Name] | [Name], Test Manager
Test Case Development: 10/10/2023 to 25/10/2023 | Test Engineer: Shahriar Farabi | [Name], Project Manager
Test Execution: [Date to Date] | Tools: | [Name], Development Lead
Bug Reporting: [Ongoing during Test Execution]
Test Summary Report: [Date]
Introduction | Objectives | Scope | Testing Data
This test plan aims to define the testing strategy and approach for the login page and footer of the TechLand BD website. This document will outline the objectives, scope, resources, testing data, test items, test approach, test deliverables, test environment, entry and exit criteria, risk and contingencies, and schedule for the testing activities, ensuring that the login and footer functionality meets the specified requirements and performs reliably under various conditions. | 1. To verify that the login page functions as expected under normal and exceptional conditions 2. To ensure that the user authentication process is secure 3. To identify and document any defects or issues in the login functionality 4. Test the login page's ability to handle invalid inputs and unexpected scenarios 5. To validate the user experience and usability of the login page | The scope of this test plan includes: 1. Usability testing and UI testing of the login interface and footer 2. Functional testing of the login page and footer 3. Negative testing to evaluate the login page's response to incorrect usernames or passwords, including special characters and excessively long inputs 4. Security testing related to the login and footer functionality
Test Items | Test Approach | Test Deliverables | Test Environment
The test items include the following components of the login page: 1. Username field 2. Password field 3. Login button 4. "Remember me" checkbox 5. "Forgotten Password" link 6. "Register Account" link 7. Error messages and validation prompts 8. Footer 9. CAPTCHA 10. Responsiveness etc. | The testing approach involves the following types of testing: Usability Testing & UI Testing: 1. Ease of use and accessibility of the login page 2. Clarity and visibility of error messages 3. User interface consistency and design adherence Functional Testing & Negative Testing: 1. Valid and invalid login attempts 2. Boundary value analysis for input fields 3. Field validation (mandatory fields, data types, character limits) Security Testing: 1. Log in notification 2. Secure password handling and transmission | 1. Test Plan 2. Mind Maps 3. Test Cases 4. Report 5. Bug Reports 6. Test Metrics | The test environment will include: 1. Web browsers: Chrome, Firefox, Safari, Edge (latest versions) 2. Operating systems: Windows 10 3. Devices: Desktop, Laptop, Tablet, Mobile
Entry Criteria | Exit Criteria | Risk and Contingencies
1. Login page development is complete | 1. All planned test cases are executed | Risk: Delays in development might impact the testing schedule
2. Test environment is set up | 2. All critical and major defects are resolved or mitigated | Mitigation: Regular status meetings with the development team
3. Test cases are reviewed and approved | 3. Test summary report is prepared and reviewed

## Mind Maps
Mindmaps for TechLand BD login page

## Test Cases
Product Name: TECHLAND | [8 empty] | TC Start Date | 2023-10-10 | TC Execution Start Date |  |  |  | TEST CASE SUMMARY
Module Name: User Management, Sign In / Register | [8 empty] | TC End Date | 25/10/2023 | TC Execution End Date |  |  |  | PASS | 38 | PASS
Epic | [8 empty] | Test Case Developed By | Shahriar Farabi | Browser (tested) | Yes |  |  | FAIL | 24 | FAIL
Developer Name (TL) : | [8 empty] | Test Case Reviewed By |  | Performance (tested) | No |  |  | Not Executed | 0 | Not Executed
Test Executed by: Shahriar Farabi | [14 empty] | Out of Scope | 0 | Out of Scope
[15 empty] | TOTAL | 62
#SL | Test Case ID/Name | Types of Testing | Module | Sub-Module | Feature | Sub-Feature | Test Case | Test Data | Reproducing Steps | Expected Result | Actual | Bug Screenshot or Video | Dev Comments | Status | Remarks
SL1 | TC001 | Browser Compatibility Testing | User Management | Sign In / Register |  |  | Checking by running the site in different browsers | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Go to different browsers 2. Search 'Techland BD' 3. Go to the website | Should run in different browsers | Found as per expectation |  |  | PASS
SL2 | TC002 | UI Testing | User Management | Sign In / Register | Login |  | Confirm all sign-in/register-related elements and fields are present on the sign-in/register page |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check all sign-in / register-related elements and fields | All sign-in / register-related elements and fields will be present on the sign-in / register page | Found as per expectation |  |  | PASS
SL3 | TC003 | [5 empty] | Ensure the font type and size of labels and text on different elements are clearly visible |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify all types of font and sizes according to the plan | Clear font type and size of the labels and the text written on the different elements will clear | Found as per expectation |  |  | PASS
SL4 | TC004 | [5 empty] | Verify that the size, color, and UI of different elements match the specified standards |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check all types of elements | All types of sizes, colors, and UI of different elements should match the specifications | Found as per expectation |  |  | PASS
SL5 | TC005 | [5 empty] | Validate that upon opening the login page, the cursor is blinking by default in the username textbox |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify whether the cursor should remain blinking on the username textbox by default or not when the login page opens | The cursor will remain blinking on the username textbox by default when the login page opens | Not found as per expectation | See video |  | FAIL
SL6 | TC006 | [5 empty] | Confirm that the password is displayed in masked form while being typed in the password field |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check if the password is in masked form or not when typing in the password field | The password will be in masked form when typed in the password field | Found as per expectation |  |  | PASS
SL7 | TC007 | [5 empty] | Ensure that the password remains hidden after submission |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter the password into the password field 4. Verify whether the password will visible or not | The password should not be visible after submission | Found as per expectation |  |  | PASS
SL8 | TC008 | [5 empty] | Validate that newsletter checkboxes are correctly displayed |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify that there are any newsletter checkbox available or not | Newsletter checkboxes are displayed without visual errors or anomalies, appearing correctly on the screen | Not found as per expectation | See screenshot |  | FAIL
SL9 | TC009 | [5 empty] | Verify that an error message appears upon entering an invalid email format or any unethical activities |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email in the email field or invalid email or unethical activities 5. Check whether the error message will display or not after entering an invalid email format or unethical activities | The error message will display after entering an invalid email format | Found as per expectation |  |  | PASS
SL10 | TC010 | [5 empty] | Check for spelling or grammatical mistakes |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check all spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation |  |  | PASS
SL11 | TC011 | [5 empty] | Ensure the presence of the eye icon next to the password field |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check eye icon is here or not | The eye icon will present next to the password field | Not found as per expectation | See screenshot |  | FAIL
SL12 | TC012 | [5 empty] | Verify that the login page UI elements are localized correctly for different languages |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Change the language setting of the application to the desired language (e.g., Spanish) | UI elements are localized correctly and display text in the selected language | Not found as per expectation | See screenshot |  | FAIL
SL13 | TC013 | [5 empty] | Confirm the correctness of the login page title |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check log in page title | Login page title should be accurate | Found as per expectation |  |  | PASS
SL14 | TC014 | [5 empty] | Verify that mandatory fields are marked with a red asterisk |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check all mandatory fields are marked with a red asterisk | Mandatory fields will be marked with a red asterisk | Not found as per expectation | See screenshot |  | FAIL
SL15 | TC015 | [5 empty] | Ensure the presence of the "Forgot Password" link |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3.Verify "Forgot Password" link is present or not | The "Forgot Password" link is present | Found as per expectation |  |  | PASS
SL16 | TC016 | [5 empty] | Validate the existence of the "Register Account" link |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check "Register Account" link is present or not | The "Register Account" link is present | Found as per expectation |  |  | PASS
SL17 | TC017 | [5 empty] | Confirm the presence of the "Log In" button |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check whether "the "Log In" button is present or not | The "Log In" button is present | Found as per expectation |  |  | PASS
SL18 | TC018 | [5 empty] | Verify the presence of the "Remember Me" checkbox | Email: kalkalkalkal@gmail.com | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check "Remember Me" checkbox is present or not | The "Remember Me" checkbox will present | Not found as per expectation | See video |  | FAIL
SL19 | TC019 | [5 empty] | Check that the "Remember Me" checkbox is not enabled by default | Email: kalkalkalkal@gmail.com | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check "Remember Me" checkbox is not enabled by default | The "Remember Me" checkbox will not enabled by default | Not found as per expectation | See video |  | FAIL
SL22 | TC020 | [5 empty] | Verify that the login page of the website is responsive and aligns properly on different screen resolutions and devices |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check log in page with multiple devices | The login page of the website will be responsive and work properly on different screen resolutions and devices | Found as per expectation |  |  | PASS
SL23 | TC021 | [5 empty] | Checking alert messages for all mandatory fields |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click a mandatory field 4. Verify that the alert message will be visible | Alert messages will displayed for all mandatory fields | Not found as per expectation | See video |  | FAIL
SL24 | TC022 | UI Testing | User Management | Sign In / Register | Login | Footer | Verify the presence of the Footer with all related elements and fields |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check if the footer is present at the bottom of the login page | The footer should be visible and positioned correctly at the bottom of the login page | Found as per expectation |  |  | PASS
SL25 | TC023 | [5 empty] | Verify Footer social media Icons |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check if social media icons (if any) are present in the footer | All specified social media icons should be present and visible in the footer | Found as per expectation |  |  | PASS
SL26 | TC024 | [5 empty] | Verify Footer Responsiveness |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check log in page with multiple devices | The footer should be responsive and display correctly across different screen sizes | Found as per expectation |  |  | PASS
SL25 | TC025 | [5 empty] | Verify Footer Accessibility |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. The footer should be accessible, with all elements properly labeled and navigable via keyboard | The footer should be accessible, with all elements properly labeled and navigable via keyboard | Found as per expectation |  |  | PASS
SL26 | TC026 | Usability Testing | User Management | Sign In / Register | Login |  | Checking copy-paste functionality in email field |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Copy and paste text in email field | Copy-paste functionality will be working for email field | Found as per expectation |  |  | PASS
SL27 | TC027 | [5 empty] | Verify that the user can navigate or access the different controls by pressing the "Tab" key on the keyboard |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter a tab in every field | "Tab" key will work | Found as per expectation |  |  | PASS
SL28 | TC028 | [5 empty] | Verify that the user is able to login by entering valid credentials and pressing "Enter" key |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your email and password 4. Verify Enter key is working to login | "Enter" key will working | Found as per expectation |  |  | PASS
SL29 | TC029 | Usability Testing | User Management | Sign In / Register | Login | Footer | Verify that the user can navigate or access the different controls by pressing the "Tab" key on the keyboard |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter a tab in footer field | "Tab" key will work | Found as per expectation |  |  | PASS
SL30 | TC030 | [5 empty] | Verify that the user is able to login by entering valid credentials and pressing "Enter" key |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify Enter key is working on footer links | "Enter" key will working | Found as per expectation |  |  | PASS
SL31 | TC031 | Functional Testing | User Management | Sign In / Register | Login |  | Verify the login screen will appear after clicking on a Sign In / Register button |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify whether the login screen will appear or not after clicking on a Sign In / Register button | The login screen should appear after clicking on a Sign In / Register button | Found as per expectation |  |  | PASS
SL32 | TC032 | [5 empty] | Verify that the user can login by entering valid data and clicking on the "Login" button |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter valid credentials 4. Check whether the Login button and login button are working or not | User can login by entring valid data | Found as per expectation |  |  | PASS
SL33 | TC033 | [5 empty] | Checking that the user is not able to login with an invalid email address and password | Email: kalkalkalkal@gmail.com | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter an invalid email address and password 4. Verify that login with an invalid email address and password is working or not | The user can not able to login with an invalid email address and password | Not found as per expectation | See video |  | FAIL
SL34 | TC034 | [5 empty] | Verify that the reset button functionality is on the login page. Clicking on it should clear the textbox’s content |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click the Sign in/Register button 3. Enter your email and password and reset it 4. Verify that the reset button functionality is available and that the user can reset it on the login page. | The reset button functionality will be available on the login page and working it properly | Not found as per expectation | See video |  | FAIL
SL35 | TC035 | [5 empty] | Verify that closing the browser should log out an authenticated user. Launching the application should lead the user to the login state only |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Close the browser and see if the account will log out or not | Closing the browser will log out an authenticated user. Launching the application will lead the user to the login state only | Not found as per expectation | See video |  | FAIL
SL36 | TC036 | [5 empty] | Verify that the system enforces a login rate limit and displays a message when the limit is exceeded |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Enter an invalid email and password 3. Click on the login button 4. Repeat steps 2-3 for a predefined number of times within a short period (e.g., 5 login attempts within 1 minute) | The system displays a message indicating the user has exceeded login attempts and may optionally implement a time-based lockout to prevent further attempts for a specified period (e.g., 5 minutes) | Not found as per expectation | See video |  | FAIL
SL37 | TC037 | [5 empty] | Inputting E-Mail Address and Password with alphanumeric characters |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address and password with alphanumeric characters | E-mail Addresses and Passwords with alphanumeric characters should work | Found as per expectation |  |  | PASS
SL38 | TC038 | [5 empty] | Enter the correct email address and password with Caps Lock enabled |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and password 5. Check the correct email address and password with Caps Lock enabled or not | Caps Lock should be working | Found as per expectation |  |  | PASS
SL39 | TC039 | [5 empty] | Verify that the 'Remember Me' checkbox can be selected and deselected on the login page |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Locate the 'Remember Me' checkbox and verify it is initially unchecked 4. Click the 'Remember Me' checkbox to select it and verify it becomes checked. 5. Click the 'Remember Me' checkbox again to deselect it and verify it returns to an unchecked state | The login page loads correctly, the 'Remember Me' checkbox toggles between checked and unchecked when clicked, and optionally retains its state after a refresh if designed to do so | Not found as per expectation | See video |  | FAIL
SL40 | TC040 | [5 empty] | Checking visiting the site again by selecting "Remember Me" |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and password 5. Check the 'Remember Me' checkbox by selecting | By selecting "Remember Me", the site should be visible again | Not found as per expectation | See video |  | FAIL
SL41 | TC041 | [5 empty] | Verify auto time-out functionality after a period of inactivity |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Open the application or navigate to the login page 3. Enter valid user credentials and log into the account 4. Start an activity timer to track user inactivity 5. Do not perform any actions (mouse movements, keyboard inputs, etc.) and wait for the inactivity period to elapse 6. Observe the system's behavior after the inactivity period elapses 7. Attempt to perform any actions (e.g., click on a link or button) after being logged out | The system should log out the user automatically after the defined period of inactivity, redirecting to the login page and requiring re-authentication for further access | Not found as per expectation | See video |  | FAIL
SL42 | TC042 | [5 empty] | Verify users can recover their password through the "Forgotten Password" option and confirm the appropriate display of the "Forgotten Password" page |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Forgotten Password" 4. Check "Forgotten Password" page will display or not when a user tries to do that | The "Forgotten Password" page should displayed | Found as per expectation |  |  | PASS
SL43 | TC043 | [5 empty] | Verify that users can successfully register a new account through the "Register Account" option and confirm that the 'Register Account' page is displayed appropriately |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Check "Register Account" page will display or not when a user tries to create a new account | The "Register Account" page should displayed | Found as per expectation |  |  | PASS
SL44 | TC044 | Functional Testing | User Management | Sign In / Register | Login | Footer | Verify Footer links |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check if all expected links are present in the footer (e.g., Privacy Policy, Terms of Service, Contact Us) | All specified links should be present and visible in the footer | Found as per expectation |  |  | PASS
SL45 | TC045 | [5 empty] | Verify Link navigation |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click on each footer link (e.g., Privacy Policy, Terms of Service, Contact Us) and verify that it navigates to the correct page | Each link should navigate to the respective pages correctly | Found as per expectation |  |  | PASS
SL46 | TC046 | [5 empty] | Verify social media links |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click on each social media icon and verify that it opens the correct social media page in a new tab/window | Each social media icon should open the respective social media page correctly | Found as per expectation |  |  | PASS
SL47 | TC047 | Negative Testing | User Management | Sign In / Register | Login |  | Verify that the validation message gets displayed in case the user leaves the email address or password field blank |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Leave the email address or password field blank 4. Check that the validation message gets displayed or not | The validation message should displayed | Found as per expectation |  |  | PASS
SL48 | TC048 | [5 empty] | Check that the validation message is displayed in case the user exceeds the character limit of the email address and password fields |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Exceeds the character limit of the email address and password fields 4. Check that the validation message gets displayed or not | The validation message should displayed | Not found as per expectation | See video |  | FAIL
SL49 | TC049 | [5 empty] | Inputting E-Mail Addresses with special characters |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address with special characters 4. Check if a pop-up message will appear or not | E-mail Addresses and Passwords with special characters should not work, a message will displayed | Not found as per expectation | See video |  | FAIL
SL50 | TC050 | [5 empty] | Inputting E-Mail Address and Password with only numbers |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address and password with only numbers 4. Check if a pop-up message will appear or not | E-mail Addresses and Passwords with only numbers should not work, a message will displayed | Not found as per expectation | See video |  | FAIL
SL51 | TC051 | [5 empty] | Inputting E-Mail Address with decimal numbers |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address with decimal numbers 4. Check if a pop-up message will appear or not | E-Mail Addresses and Passwords with decimal numbers should not work, a message will displayed | Not found as per expectation | See video |  | FAIL
SL52 | TC052 | [5 empty] | Entering comma between alphabets for E-Mail Address and Password |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter a comma between alphabets for an e-mail address and password 4. Check whether a pop-up message will appear or not | A comma between alphabets or only comma for E-Mail Address and Password should not work, a message will displayed | Not found as per expectation | See video |  | FAIL
SL53 | TC053 | [5 empty] | Entering space between alphabets for E-Mail Address and Password |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter space between alphabets for e-mail address and password 4. Check if a pop-up message will appear or not | Space between alphabets for the E-Mail Address and Password should not work, a message will displayed | Not found as per expectation | See video |  | FAIL
SL54 | TC054 | [5 empty] | Verify that the error message displays after entering an unregistered email address |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Verify that the error message will display or not after entering an unregistered email address | The error message should display after entering an unregistered email address | Not found as per expectation | See video |  | FAIL
SL55 | TC055 | [5 empty] | Leave the email field blank and enter a valid password |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave the email field blank and enter a valid password 5. An error message will display or not | An error message will appear | Found as per expectation |  |  | PASS
SL56 | TC056 | [5 empty] | Enter a valid email address and leave the password field blank |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email field and enter without password 5. An error message will display or not | An error message will appear | Found as per expectation |  |  | PASS
SL57 | TC057 | [5 empty] | Enter a valid email address with an incorrect password |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and enter an incorrect password 5. A password incorrect message will display or not | An "incorrect password" message will appear | Found as per expectation |  |  | PASS
SL58 | TC058 | Security Testing | User Management | Sign In / Register | Login |  | Checking login notification sent to the registered email |  | 1. Go to the URL: https://www.techlandbd.com/. 2. Click on the Sign In/ Register button 3. Click "Login" after entering the email and password. 4. Check the login notification sent to the registered email | A mail will appear to the email address | Not found as per expectation | See screenshot |  | FAIL
SL59 | TC059 | [5 empty] | Verify a captcha will be visible if the password is wrong multiple times |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and password 5. Verify whether a captcha will be visible or not if the password is wrong | A captcha should be visible if the password is wrong | Not found as per expectation | See video |  | FAIL
SL60 | TC060 | [5 empty] | Checking the password can't be copy-pasted |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter a password in the password field 4. Check the password can't be copy-pasted or not | The password can't be copy-pasted | Found as per expectation |  |  | PASS
SL61 | TC061 | Security Testing | User Management | Sign In / Register | Login | Footer | Verify Secure Link Navigation |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify that all footer links use HTTPS protocol and lead to secure pages | All footer links should use HTTPS protocol, ensuring secure navigation | Found as per expectation |  |  | PASS
SL62 | TC062 | [5 empty] | Verify Security of External Links |  | 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Ensure that external links (e.g., social media) open in a new tab/window to prevent security risks | External links should open in a new tab/window for security reasons | Found as per expectation |  |  | PASS
[6 empty] | Improvement Scopes | "Remember Me" checkbox should be selected according to user
A maximum length of the password should be defined
"Sign in with Facebook" should be available on the login page
"Sign in with Google" should be available on the login page

## Report
Test Case Report
Project Name | TECHLAND
Module Name | User Management, Sign In / Register |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 38 | PASS
Written By | Shahriar Farabi |  |  |  |  | 24 | FAIL
Executed By | Shahriar Farabi |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
62 | 38 | 24 | 0 | 0 | 62
Grand Total | 38 | 24 | 0 | 0 | 62
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Reports
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL5 | # SL8 | # SL11 | # SL12 | # SL14 | # SL18 | # SL19 | # SL21
Issue: The cursor doesn't remain blinking in the username textbox by default when the login page opens | Issue: Checkboxes are not displayed correctly | Issue: The eye icon is not present next to the password field | Issue: There is no language changing option | Issue: Mandatory fields will be marked with a red asterisk but not found as expected | Issue: The "Remember Me" checkbox is not present | Issue: The "Remember Me" checkbox is not enabled by default but there is no "Remember Me" checkbox | Issue: There is no alert messages for all mandatory fields
Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify whether the cursor should remain blinking on the username textbox by default or not when the login page opens | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Verify that there are any newsletter checkboxes available or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check eye icon is here or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Change the language setting of the application to the desired language (e.g., Spanish) | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check all mandatory fields are marked with a red asterisk | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check "Remember Me" checkbox is present or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Check that the "Remember Me" checkbox is not enabled by default | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click a mandatory field 4. Verify that the alert message will be visible or not
Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production
Module: User Management | Module: User Management | Module: User Management | Module: User Management | Module: User Management | Module: User Management | Module: User Management Sub-Module: Sign In / Register | Module: User Management Sub-Module: Sign In / Register
Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register
Severity: P2 | Severity: P2 | Severity: P2 | Severity: P2 | Severity: P2 | Severity: P2 | Severity: P2 | Severity: P2
See video | See screenshot | See screenshot | See screenshot | See screenshot | See video | See video | See video
Expected: The cursor will remain blinking on the username textbox by default when the login page opens | Expected: Newsletter checkboxes are displayed without visual errors or anomalies, appearing correctly on the screen | Expected: The eye icon will present next to the password field | Expected: UI elements are localized correctly and display text in the selected language | Expected: Mandatory fields will be marked with a red asterisk | Expected: The "Remember Me" checkbox will present | Expected: The "Remember Me" checkbox will not enabled by default | Expected: Alert messages will displayed for all mandatory fields
Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL33 | # SL34 | # SL35 | # SL36 | # SL39 | # SL40 | # SL41
Issue: The user can log in with an invalid email address and password | Issue: The reset button functionality is missing | Issue: Closing the browser should log out an authenticated user, and launching the application should direct the user to the login state exclusively, which is not happening as expected | Issue: The system should enforce a login rate limit and display a message when the limit is exceeded, but this is not occurring as expected | Issue: Verify that the 'Remember Me' checkbox can be selected and deselected on the login page | Issue: When revisiting the site after selecting "Remember Me," the system should automatically log you in without requiring you to enter your credentials again | Issue: The auto time-out functionality, which should log out users after a period of inactivity, is not working as expected
Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter an invalid email address and password 4. Verify that login with an invalid email address and password is working or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click the Sign in/Register button 3. Enter your email and password and reset it 4. Verify that the reset button functionality is available and that the user can reset it on the login page | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Close the browser and see if the account will log out or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Enter an invalid email and password combination 3. Click on the login button 4. Repeat steps 2-3 for a predefined number of times within a short period (e.g., 5 login attempts within 1 minute) | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Locate the 'Remember Me' checkbox and verify it is initially unchecked 4. Click the 'Remember Me' checkbox to select it and verify it becomes checked. 5. Click the 'Remember Me' checkbox again to deselect it and verify it returns to an unchecked state | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and password 5. Check the 'Remember Me' checkbox by selecting | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Open the application or navigate to the login page 3. Enter valid user credentials and log into the account 4. Start an activity timer to track user inactivity 5. Do not perform any actions (mouse movements, keyboard inputs, etc.) and wait for the inactivity period to elapse 6. Observe the system's behavior after the inactivity period elapses 7. Attempt to perform any actions (e.g., click on a link or button) after being logged out
Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register
Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P2 | Severity: P1 | Severity: P1
See video | See video | See video | See video | See video | See video | See video
Expected: The user can not able to login with an invalid email address and password | Expected: The reset button functionality will be available on the login page and working it properly | Expected: Closing the browser will log out an authenticated user. Launching the application will lead the user to the login state only | Expected: The system displays a message indicating the user has exceeded login attempts and may optionally implement a time-based lockout to prevent further attempts for a specified period (e.g., 5 minutes) | Expected: The login page loads correctly, the 'Remember Me' checkbox toggles between checked and unchecked when clicked, and optionally retains its state after a refresh if designed to do so | Expected: By selecting "Remember Me", the site should be visible again | Expected: The system should log out the user automatically after the defined period of inactivity, redirecting to the login page and requiring re-authentication for further access
Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi
Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting | Bug Reporting
# SL48 | # SL49 | # SL50 | # SL51 | # SL52 | # SL53 | # SL54
Issue: The validation message is not displayed when the user exceeds the character limit for the email address and password fields | Issue: Inputting email addresses with special characters should trigger an error message | Issue: Inputting an email address and password with only numbers should trigger an error message or be rejected as invalid input | Issue: Inputting an email address with decimal numbers should prompt an error message | Issue: Entering a comma between alphabets for the email address and password should result in an error message being displayed | Issue: Entering a space between alphabets for the email address and password should trigger an error message | Issue: An error message should display after entering an unregistered email address but not showing
Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Exceeds the character limit of the email address and password fields 4. Check that the validation message gets displayed or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address with special characters 4. Check if a pop-up message will appear or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address and password with only numbers 4. Check if a pop-up message will appear or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter your e-mail address with decimal numbers 4. Check if a pop-up message will appear or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter a comma between alphabets for an e-mail address and password 4. Check whether a pop-up message will appear or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Enter space between alphabets for e-mail address and password 4. Check if a pop-up message will appear or not | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Verify that the error message will display or not after entering an unregistered email address
Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production | Environment: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up | Module: Sign Up
Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register | Sub-Module: Sign In / Register
Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1 | Severity: P1
See video | See video | See video | See video | See video | See video | See video
Expected: The validation message should displayed | Expected: E-mail Addresses and Passwords with special characters should not work, a message will displayed | Expected: E-mail Addresses and Passwords with only numbers should not work, a message will displayed | Expected: E-Mail Addresses and Passwords with decimal numbers should not work, a message will displayed | Expected: A comma between alphabets or only comma for E-Mail Address and Password should not work, a message will displayed | Expected: Space between alphabets for the E-Mail Address and Password should not work, a message will displayed | Expected: The error message should display after entering an unregistered email address
Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi
Bug Reporting | Bug Reporting
# SL58 | # SL59
Issue: No login notification was sent to the registered email as expected | Issue: A CAPTCHA should be displayed if the wrong password is entered multiple times
Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/. 2. Click on the Sign In/ Register button 3. Click "Login" after entering the email and password 4. Check all types of valid credentials | Reproducing Steps: 1. Go to the URL: https://www.techlandbd.com/ 2. Click on the Sign In/ Register button 3. Click "Register Account" 4. Leave an email and password 5. Verify whether a captcha will be visible or not if the password is wrong
Environment: Production | Environment: Production
Module: Sign Up | Module: Sign Up
Sub-Module: Sign In / Register | Sub-Module: Sign In / Register
Severity: P1 | Severity: P1
See screenshot | See video
Expected: A mail will appear to the email address | Expected: A captcha should be visible if the password is wrong
Responsible QA: Shahriar Farabi | Responsible QA: Shahriar Farabi

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (62/62)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/62)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (38/62)*100 = 61.29
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (24/62)*100 = 38.71
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A